## Sheet1
Studio Name: | Fishbowl 3D | First Name | Surname | Pnumber | Roles
Team Size: | Six | Dylan | Mather | P2717379 | Buildings and Track Design
|  | Cassidy | Tacey | P2717399 | Landscape props
|  | Gary | Dobedo | P2720295 | Cars and Track Modelling
|  | David | Gandy | P2768772 | Terrain Modelling
|  | William | Murfit | P2727010 | Machinery props modelling
|  | Grace | Harris |  | Concept Art

## Sheet2
Sprint Start: | 2024-12-02
Sprint End: | 2024-12-08
Sprint Objectives
Objective |  | Allocated to | Objective Met?
Set up Github Repository |  | Dylan Mather
Concept Art |  | Grace Harris
Terrain blockout |  | David Gandy
Block out Car model |  | Gary Dobedo
Landscape prop layout |  | Cassidy Tacey
Blocking out larger machinery |  | Will Murfit
Problem Areas

## Sheet3
Fishbowl 3D
Task Name | Priority | Status | Assaigned To | Date Started | Date Finished | Key | Meaning
Sprint 1 | High | Complete | Grace | 2024-02-12 | 2024-09-12 | Block Out | Model using primative shapes only
Set up GitHub | High | Complete | Dylan | 2024-02-12 | 12/03/2024 | BO | Acronym for Block Out
Terrain Landscape | Medium | In Progress | David | 2024-02-12 | Rollover | 1st Iteration | A model with more details added after block out
Block Out Car | Low | Complete | Gary | 2024-02-12 | 2024-05-12 | 2nd Iteration | A fully complete model ready for texturing
Concept Art | High | Not Started | Grace | 2024-02-12 | Rollover | Itrn | Acronym for Iteration
Machine Block Out | Low | Complete | Will | 2024-02-12 | 2034-09-12 | Christmas | Christmas Break, less work was complete
Landscape Block | High | In Progress | Cas | 2024-02-12 | Rollover | Rollover | A task that has taken longer than the initial deadline
Sprint 2 | High | Complete | Cas | 2024-09-12 | 12/16/2024 |  | which is then rolled over to the following week
Track Design & 1st Itrn | High | Complete | Dylan and Cas | 2024-09-12 | 2024-12-12 | Low | A task which does not affect the workflow of the project
Residential 1st Iteration | Medium | Complete | Will | 2024-09-12 | 12/13/2024 |  | if it takes longer than its deadline
Nuclear 1st Iteration | Medium | Complete | Dylan | 2024-09-12 | 12/14/2024 | Medium | A task that needs to be done but is not urgent
Skyscrapers Block | Medium | Complete | Cas and Will | 2024-09-12 | 12/13/2024 | High | A task which is urgent and workflow depends on it being complete
Modular Items 1st Iteration | Low | Complete | Cas | 2024-09-12 | 12/12/2024 | Very High | A task which needs to be prioritsed above everything
Car 1st Iteration | Low | Complete | Gary | 2024-09-12 | 12/12/2024 | C | A task which is completed by some of the people it was assaingend to
Horizon decision | High | Complete | Everyone | 2024-09-12 | 12/14/2024 | IP | A task which Is in progress by one person when assigned to a group
Concept Art | Very High | Complete | Grace | 2024-02-12 | 12/10/2024
Landscape Block | Very High | Complete | Cas | 2024-02-12 | 12/10/2024
Terrain Landscape | Very High | Complete | David | 2024-02-12 | 12/13/2024
Mechanical Items 1st Itrn | Low | Complete | Will | 2024-12-12 | 12/14/2024
Sprint 3 | High | Complete | Cas | 12/16/2024 | 12/23/2024
Nuclear Props 2nd Itrn | Low | Complete | Cas | 12/16/2024 | 12/22/2024
Horizon Block Out | Medium | Complete | Dylan | 12/16/2024 | 12/19/2024
Landscape 1st Iteration | Medium | Complete | Cas | 12/16/2024 | 12/18/2024
Con Vehciles Block | Low | In Progress | Gary | 12/16/2024 | Rollover
Skyscrapers 1st Itrn | Low | Complete | Cas and Will | 12/16/2024 | 12/20/2024
Sprint 4 (Christmas) | High | Complete | Cas | 12/23/2024 | 12/30/2024
Landscape 2nd Iteration | Medium | In Progress | Cas and David | 12/23/2024 | Rollover
Car Varieties Block | Medium | In Progress | Everyone | 12/23/2024 | Rollover
Con Vehciles Block | Low | In Progress | Gary | 12/16/2024 | Rollover
Sprint 5(Christmas) | High | Complete | Cas | 12/30/2024 | 01/6/2025
Horizon 1st Itrn | Medium | Complete | Dylan | 12/30/2024 | 2025-03-01
Con Vehciles Block | High | Complete | Gary | 12/16/2024 | 2025-06-01
Car Varieties 1st Itrn | Medium | Complete | Everyone | 12/30/2024 | 2025-05-01
Sprint 6 | High | Complete | Cas | 01/6/2025 | 01/13/2025
Track 2nd Iteration | High | Complete | Dylan | 2025-06-01 | 2025-09-01
Nuclear 2nd Iteration | Very High | In Progress | Cas | 2025-06-01 | Rollover
CityScape 2nd Iteration | Very High | In Progress | Cas | 2025-06-01 | Rollover
Lava Lake | Medium | Complete | David | 2025-06-01 | 2025-10-01
Landscape Texture 1st Itrn | Medium | In Progress | David and Cas | 2025-06-01 | Rollover
Con Vehicles 2nd Itrn | High | In Progress | Gary | 2025-06-01 | Rollover
Skyscrapers 2nd Itrn | High | Done | Will, Cas and Gary | 2025-06-01 | 2025-10-01
Landscape 2nd Itrn | High | Done | David and Cas | 12/23/2024 | 2025-11-01
Mechanical Items 2nd Itrn | Low | Complete | Will | 2025-06-01 | 01/11/2025
Horizon 2nd Itrn | Medium | In Progress | Dylan | 12/30/2024 | Rollover
Sprint 7 | High | Complete | Cas | 01/13/2025 | 01/20/2025
Nuclear 2nd Iteration | Very High | Complete | Cas | 2025-06-01 | 01/17/2025
CityScape 2nd Iteration | Very High | In Progress | Cas | 2025-06-01 | Rollover
Landscape Texture 1st Itrn | Very High | Complete | David | 2025-06-01 | 01/14/2025
Con Vehicles 2nd Itrn | High | In Progress | Gary | 2025-06-01 | Rollover
Horizon 2nd Itrn | Medium | Complete | Dylan | 2025-06-01 | 01/15/2025
Landscape Texture 2nd Itrn | High | In Progress | Cas and David | 01/13/2025 | Rollover
Racing Vehicles Final Itrn | Medium | In Progress | Dylan | 01/13/2025 | Rollover
Con Vehciles Final Itrn | Medium | In Progress | Gary | 01/13/2025 | Rollover
Modular Items Final Itrn | High | In Progress | Cas | 01/13/2025 | Rollover
Sign Texturing | Low | In Progress | Dylan | 01/13/2025 | Rollover
Start Track | Very High | Not Started | Grace | 01/13/2025 | Rollover
Nuclear Props Final Itrn | High | In Progress | Cas | 01/13/2025 | Rollover
Skyscrapers Final Itrn | High | In Progress | Gary Cas and Will | 01/13/2025 | Rollover
Track Final Itrn | High | Complete | Dylan | 01/13/2025 | 01/16/2025
Sprint 8 | High | Complete | Cas | 01/20/2025 | 01/27/2025
CityScape 2nd Iteration | Very High | Complete | Cas | 2025-06-01 | 01/22/2025
Con Vehicles 2nd Itrn | Very High | Complete | Gary | 2025-06-01 | 01/23/2025
Landscape Texture 2nd Itrn | High | Complete | David | 01/13/2025 | 01/20/2025
Racing Vehicles Final Itrn | High | Complete | Dylan | 01/13/2025 | 01/21/2025
Modular Items Final Itrn | High | Complete | Cas | 01/13/2025 | 01/23/2025
Sign Texturing | High | In Progress | Grace | 01/13/2025 | Rollover
Start Track | Very High | In Progress | Grace | 01/13/2025 | Rollover
Nuclear Props Final Itrn | High | Complete | Cas | 01/13/2025 | 01/25/2025
Skyscrapers Final Itrn | High | Complete/in progress | Cas/Will. -C. Gary, IP | 01/13/2025 | 01/26/2025 Rollover
Mechanical Items Final Itrn | High | In Progress | Will | 01/20/2025 | Rollover
Con Vehicles Final Itrn | Very High | In Progress | Gary | 01/20/2025 | Rollover
Sprint 9 | High | Complete | Cas | 01/27/2025 | 01/29/2025
Con Vehicles Final Itrn | Very High | In Progress | Gary | 01/20/2025 | 01/27/2025
Sign Texturing | High | Complete | Grace | 01/13/2025 | 01/26/2025
Skyscrapers Final Itrn | High | In Progress | Gary | 01/13/2025 | Not Completed
Nuclear Final Itrn | Very High | Complete | Will, Cas, David, Dylan | 01/27/2025 | 01/29/2025
CityScape Final Itrn | Very High | Complete | Will, Cas, David, Dylan | 01/27/2025 | 01/29/2025
Landscape Texture Final Itrn | Very High | Complete | David | 01/27/2025 | 01/28/2025
Landscape Final Itrn | Very High | Complete | Will, Cas, David, Dylan | 01/27/2025 | 01/29/2025
Lighting | Very High | Complete | Dylan and David | 01/27/2025 | 01/28/2025
Special Effects | Medium | Complete | Dylan | 01/27/2025 | 01/28/2025
Mechanical Items Final Itrn | High | In Progress | Will | 01/20/2025 | 01/27/2025